## Excel
Project Summary Cost
|  | Labor Total (Approximate) | [5 empty] | 25226.77
|  | Furniture and Equipment | [5 empty] | 57575
|  | Project Total (Approximate) | [5 empty] | 82801.77
Labor Cost
Hourly Rate
| Project Manager |  |  |  |  | 50
| Lynn Bovi |  |  |  |  | 41
| Nick Johansen |  |  |  |  | 35
| Samantha Jones |  |  |  |  | 33
| Gianna Vasallo |  |  |  |  | 45
| Bob Smith |  |  |  |  | 37
[5 empty] | Average | 40.1667
Project Requirement | [5 empty] | Times (hrs) | Hourly Rate | Approximate Cost
| Develop Project Charter |  |  |  |  | 8 | 40.17 | 321.36
| Meet in Conference Room |  |  |  |  | 2 | 40.17 | 80.34
| Conduct Site Survey |  |  |  |  | 1 | 40.17 | 40.17
| Project Charter Approved |  |  |  |  | 3 | 40.17 | 120.51
| Hold Team Meeting |  |  |  |  | 2 | 40.17 | 80.34
| Check Design of Existing Furniture |  |  |  |  | 2 | 40.17 | 80.34
| Contact Procurement Department |  |  |  |  | 1 | 40.17 | 40.17
| Determine Furniture Supplier |  |  |  |  | 3 | 40.17 | 120.51
| Design Cable Path |  |  |  |  | 4 | 40.17 | 160.68
| Specify 8gb Ram card |  |  |  |  | 2 | 40.17 | 80.34
| Specify Intel core i5-650 CPU |  |  |  |  | 2 | 40.17 | 80.34
| Specify 500W Power Supply |  |  |  |  | 2 | 40.17 | 80.34
| Specify 18inch Monitor |  |  |  |  | 2 | 40.17 | 80.34
| Specify Kyocera multi-functional color network printer-copier |  |  |  |  | 2 | 40.17 | 80.34
| Specify Cisco ME3400 aggregation switch |  |  |  |  | 2 | 40.17 | 80.34
| Specify Cisco Aironet wireless access points |  |  |  |  | 2 | 40.17 | 80.34
| Specify VoIP handsets |  |  |  |  | 2 | 40.17 | 80.34
| Specify Wall-mount patch panel |  |  |  |  | 2 | 40.17 | 80.34
| Specify Network Wall Jacks |  |  |  |  | 2 | 40.17 | 80.34
| Specify Windows 10 EnterSearch Windows 10 Enterprise operating system |  |  |  |  | 1 | 40.17 | 40.17
| Specify Microsoft Office Professional 2016 Suite |  |  |  |  | 1 | 40.17 | 40.17
| Specify Microsoft Security Essentials |  |  |  |  | 1 | 40.17 | 40.17
| Specify Adobe Creative Cloud |  |  |  |  | 1 | 40.17 | 40.17
| Design Blueprint of Installation |  |  |  |  | 4 | 40.17 | 160.68
| Hold Team Meeting |  |  |  |  | 2 | 40.17 | 80.34
| Order Furniture |  |  |  |  | 2 | 40.17 | 80.34
| Order Cabling |  |  |  |  | 2 | 40.17 | 80.34
| Order 8gb Ram card |  |  |  |  | 1 | 40.17 | 40.17
| Order Intel core i5-650 CPU |  |  |  |  | 1 | 40.17 | 40.17
| Order 500W Power Supply |  |  |  |  | 1 | 40.17 | 40.17
| Order 18inch Monitor |  |  |  |  | 1 | 40.17 | 40.17
| Order Kyocera multi-functional color network printer-copier |  |  |  |  | 1 | 40.17 | 40.17
| Order Cisco ME3600 aggregation switch |  |  |  |  | 1 | 40.17 | 40.17
| Order Cisco Aironet wireless access points |  |  |  |  | 1 | 40.17 | 40.17
| Order VoIP handsets |  |  |  |  | 1 | 40.17 | 40.17
| Order Wall-mount patch panel |  |  |  |  | 1 | 40.17 | 40.17
| Order Network Wall Jacks |  |  |  |  | 1 | 40.17 | 40.17
| Order Windows 10 Enterprise operating system |  |  |  |  | 1 | 40.17 | 40.17
| Order Microsoft Office Professional 2016 Suite |  |  |  |  | 1 | 40.17 | 40.17
| Order Microsoft Security Essentials |  |  |  |  | 1 | 40.17 | 40.17
| Order Adobe Creative Cloud |  |  |  |  | 1 | 40.17 | 40.17
| Hold Team Meeting |  |  |  |  | 2 | 40.17 | 80.34
| Receive Furniture |  |  |  |  | 3 | 40.17 | 120.51
| Receive Cabling |  |  |  |  | 1 | 40.17 | 40.17
| Receive PC Workstations with monitors and software suite |  |  |  |  | 1 | 40.17 | 40.17
| Receive Kyocera multi-functional color network printer-copier |  |  |  |  | 1 | 40.17 | 40.17
| Receive Cisco ME3600 aggregation switch |  |  |  |  | 1 | 40.17 | 40.17
| Receive Cisco Aironet wireless access points |  |  |  |  | 1 | 40.17 | 40.17
| Receive VoIP handsets |  |  |  |  | 1 | 40.17 | 40.17
| Receive Wall-mount patch panel |  |  |  |  | 1 | 40.17 | 40.17
| Receive Network Wall Jacks |  |  |  |  | 1 | 40.17 | 40.17
| Inspect Furniture |  |  |  |  | 4 | 40.17 | 160.68
| Inspect Cabling |  |  |  |  | 4 | 40.17 | 160.68
| Inspect 8gb Ram card |  |  |  |  | 3 | 40.17 | 120.51
| Inspect Intel core i5-650 CPU |  |  |  |  | 3 | 40.17 | 120.51
| Inspect 500W Power Supply |  |  |  |  | 3 | 40.17 | 120.51
| Inspect 18inch Monitor |  |  |  |  | 3 | 40.17 | 120.51
| Inspect Kyocera multi-functional color network printer-copier |  |  |  |  | 3 | 40.17 | 120.51
| Inspect Cisco ME3600 aggregation switch |  |  |  |  | 3 | 40.17 | 120.51
| Inspect Cisco Aironet wireless access points |  |  |  |  | 3 | 40.17 | 120.51
| Inspect VoIP handsets |  |  |  |  | 3 | 40.17 | 120.51
| Inspect Wall-mount patch panel |  |  |  |  | 2 | 40.17 | 80.34
| Inspect Network Jacks |  |  |  |  | 2 | 40.17 | 80.34
| Inspect Windows 10 Enterprise operating system |  |  |  |  | 2 | 40.17 | 80.34
| Inspect Microsoft Office Professional 2016 Suite |  |  |  |  | 2 | 40.17 | 80.34
| Inspect Microsoft Security Essentials |  |  |  |  | 2 | 40.17 | 80.34
| Inspect Adobe Creative Cloud |  |  |  |  | 2 | 40.17 | 80.34
| Hold Team Meeting |  |  |  |  | 3 | 40.17 | 120.51
Installation and Test
| Install Furniture |  |  |  |  | 20 | 40.17 | 803.4
| Install Cabling |  |  |  |  | 25 | 40.17 | 1004.25
| Install 8gb Ram card |  |  |  |  | 5 | 40.17 | 200.85
| Install Intel core i5-650 CPU |  |  |  |  | 5 | 40.17 | 200.85
| Install 500W Power Supply |  |  |  |  | 5 | 40.17 | 200.85
| Install 18inch Monitor |  |  |  |  | 5 | 40.17 | 200.85
| Install Software |  |  |  |  | 20 | 40.17 | 803.4
| Install Network Jacks |  |  |  |  | 8 | 40.17 | 321.36
| Install Wall-mount patch panel |  |  |  |  | 8 | 40.17 | 321.36
| Connect PC with Main Server |  |  |  |  | 18 | 40.17 | 723.06
| Install VoIP handsets |  |  |  |  | 15 | 40.17 | 602.55
| Connect VoIP handsets with PBX |  |  |  |  | 18 | 40.17 | 723.06
| Install Printer |  |  |  |  | 8 | 40.17 | 321.36
| Connect Old Switch to New Switch |  |  |  |  | 15 | 40.17 | 602.55
| Install Wireless Access Points |  |  |  |  | 20 | 40.17 | 803.4
| Ensure Furniture condition |  |  |  |  | 20 | 40.17 | 803.4
| Test Cabling |  |  |  |  | 20 | 40.17 | 803.4
| Test 8gb Ram card |  |  |  |  | 5 | 40.17 | 200.85
| Test Intel core i5-650 CPU |  |  |  |  | 5 | 40.17 | 200.85
| Test 500W Power Supply |  |  |  |  | 5 | 40.17 | 200.85
| Test 18inch Monitor |  |  |  |  | 5 | 40.17 | 200.85
| Ensure Software Installation |  |  |  |  | 25 | 40.17 | 1004.25
| Test Network Jacks |  |  |  |  | 5 | 40.17 | 200.85
| Test Wall-mount patch panel |  |  |  |  | 5 | 40.17 | 200.85
| Test Connection between PC and Main Server |  |  |  |  | 20 | 40.17 | 803.4
| Test VoIP handsets |  |  |  |  | 16 | 40.17 | 642.72
| Test Connection between VoIP handsets and PBX |  |  |  |  | 15 | 40.17 | 602.55
| Test Printer |  |  |  |  | 5 | 40.17 | 200.85
| Test Connection between Old Switch with New Switch |  |  |  |  | 25 | 40.17 | 1004.25
| Test Network System |  |  |  |  | 25 | 40.17 | 1004.25
| Test Firewall |  |  |  |  | 25 | 40.17 | 1004.25
| Final Check |  |  |  |  | 40 | 40.17 | 1606.8
| Hold Team Meeting |  |  |  |  | 2 | 40.17 | 80.34
Close-Out
| Seek Sponsor Approval |  |  |  |  | 3.5 | 40.17 | 140.6
| Seek Stakeholder Approval |  |  |  |  | 3.5 | 40.17 | 140.6
| Create Project Final Report |  |  |  |  | 9 | 40.17 | 361.53
| Present Project Final Report |  |  |  |  | 2 | 40.17 | 80.34
| Upload Records to Archive |  |  |  |  | 10 | 40.17 | 401.7
| Reassign Team Member |  |  |  |  | 2 | 40.17 | 80.34
| Close the Project |  |  |  |  | 1 | 40.17 | 40.17
|  |  | Labor Total | (Approximate) |  | 628 | 40.17 | 25226.77
|  |  | Labor Total | (High) |  |  | 33 | 20724
|  |  | Labor Total | (Low) |  |  | 50 | 31400
Equipment and Furniture Cost
[6 empty] | Number | Cost (each | Total
| PC's with Software and Monitor |  |  |  |  | 15 | 1750 | 26250
| VoIP handsets |  |  |  |  | 15 | 345 | 5175
| Patch Cables (total) |  |  |  |  | 1 | 275 | 275
| Cubicle Furniture |  |  |  |  | 15 | 1300 | 19500
| Kyocera Network Printer |  |  |  |  | 1 | 3750 | 3750
| Cisco Wireless Access Points |  |  |  |  | 2 | 225 | 450
| Cisco ME3400 Switch |  |  |  |  | 1 | 1750 | 1750
| Wall-mount patch panel |  |  |  |  | 1 | 175 | 175
| Network Wall Jacks |  |  |  |  | 1 | 250 | 250
|  | Equiment and Furniture Total | [5 empty] | 57575